## Sheet1
DRAFT - 2024-25 Fiscal Year Internal Audit, Risk Management, and Compliance Activity Plan
Project Description | Company Contact | Auditor | Hours To Complete | Location | Audit Budget Impact | Planned Audit Period | Objective/Status | Risk Management Impact
Internal Audits
Support State Auditor and BOG Audits | CFO | Audit Exec | 120 | Finance | 0 | February through April | Support seamless completion of State Auditor Financial Statement audit as well as BOG audit requests. | Ensure good standing with State Auditor's office and Board of Governors with timely and complete request responses and reliable identified deficiency remediation.
Student Athletics Scholarship | Director of Enrollment | Audit Exec | 200 | Admissions Department | 0 | September | Confirm compliance with Title IX and other regulations applicable to the granting of student athletic scholarships. | Personnel do not understand compliance requirements resulting in the violation of laws or regulations, fines, and adverse publicity.
IT General Control and Cyber Security Audit, including Access Security | Chief Information Security Officer (CISO) | Audit Exec | 120 | Campus wide IT Resources | 20000 | December | Confirm the design and effectiveness of IT general controls and security measures, including SOC2 reports from 3rd parties. Conduct phishing vulnerability test to enhance access security. Confirm effective data back-up and recovery protocols are in place | Reduce risk of cyber breach and data ransom including interruption in access to, corruption of, or loss of university data processing systems and/or critical information. Avoid reputation damage.
Follow-up Prior Audit Report Findings including Post Tenure Review | Various | Audit Exec | 120 | Campus wide | 0 | Depends on Auditee's Remediation Timeline | Evaluate the extent to which reported findings have been remediated. | Improve the control environment to help prevent fraud, improve compliance and assure the achievement of the university's strategic goals.
Fixed Asset Audit Including Attractive Assets | Controller | Audit Exec | 120 | Campus wide | 0 | August | Evaluate controls over the ledgering, depreciation, and periodic inventory of fixed assets. Trace location of recent attractive asset purchases. | Mitigate the risk that university property is misappropriated and fixed asset depreciation is mistated in the financial statements.
Pcard Card Charges and Vendor Use Audit | CFO | Audit Exec | 120 | Procurement & Accounts Payable | 0 | February | Review executive and other material Pcard user expense report statements for inappropriate expenditures. Confirm controls are operating effectively. Identify any trends in vendor preferences in the past three fiscal years. | The ongoing expenditure review will help mitigate the risk of significant policy violations, adverse public image, and fraud/whistleblower investigation.
Compliance Activities
Performance Funding Metrics | CFO | Mauldin & Jenkins Audit Exec | 80 | Remote | 22000 | November through March | Audit to confirm the reliable, complete, accurate and timely reporting of data submissions to the Board of Governors in support the Performance Funding Metrics model. | Assure compliance with Board of Governor's Regulation 5.001, Performance-based Funding, requirement for an annual audit.
Work with Compliance Partners on Annual Compliance Reports and Implementation of new laws and regulations. | President's Cabinet | Audit Exec | 120 | Various | 0 | July through September | Work with thirteen university Compliance Partners to prepare annual audit reports, resolve obstacles, and promote compliance. Support General Counsel and leadership team with implementation of new compliance laws and Board of Governor regulations. | Reduce risk of undetected compliance issues.
Follow-up on Process Control Evaluation Recommendations | Human Resources, Enrollment, Student Gov't | Audit Exec | 40 | Various | 0 | September through December | Support development of integrated process controls that assure student applications are evaluated timely, without bias, and in support of the achievement of Performance Funding metrics. | Avoid repeat allegations of misconduct and a second external investigation.
Develop and implement new regulations as BOG, State, and Federal regulations change. | General Counsel | Audit Exec | 40 | Remote | 0 | Ongoing | Develop university regulations to mirror new or changed Board of Governor (BOG), state, or Federal regulations and statutes. | Avoid regulatory agency compliance or legal issues.
Annual Review of Consumer Information and other Key Website Information and Links | President's Cabinet | Audit Exec | 24 | Remote | 0 | April | Confirm all compliance information links are functioning, information is current, information is accessible to hearing impaired, and all required sites are listed. | Avoid regulatory agency compliance or legal issues.
Evaluate University's Employee Compliance Training Program | Chief Human Resources Officer | Audit Exec | 120 | Remote | 0 | July through September | Confirm university's employee training program includes all required Federal, State, and BOG required new employee and refresher training. Confirm all employees participate in training as scheduled. | Avoid legal action, sanctions, and losses associated with compliance violations or inappropriate acts performed by university employees.
Evaluate NAIA Conference Compliance | Athletics Director | Audit Exec | 160 | Cook Hall | 0 | October | Confirm athletics compliance personnel in place have strong NAIA conference knowledge and independence. Confirm compliance with conference rules. | Help the university avoid sanctions and negative press from NAIA conference rule violations.
Risk Management
Evaluate Insurance Coverages and Compliance | CFO | Audit Exec | 16 | Health & Safety Dept | 0 | December | Support the evaluation of exposures and utilization of insurance coverage as a means of transferring risk. Follow-up on Division of Risk Management report findings. | Losses from operational exposures can be mitigated through the cost effective transfer of risks to insurance pools/coverages.
Maintain COSO Based Enterprise Risk Assessment and Planning (ERM) Model. Add Website and Awareness Training | President's Cabinet | Audit Exec | 120 | Various | 0 | Ongoing | Ongoing risk management meetings with executive management, monitoring changes in key business processes, and tracking economic trends helps facilitates management’s achievement of strategic objectives and minimize the impact of adverse market changes/occurrences. ERM Program implementation continues with creation of a Governance, Risk and Control (GRC) evaluation using the COSO 2017 Integrated Framework. | An enterprise risk management program is required by the Board of Governors for all universities. Program assures significant exposures are cost effectively mitigated and changes in risk are monitored and appropriately responded to.
Succession Planning Evaluation | President's Cabinet | Audit Exec | 40 | All Areas | 0 | March | Minimize the impact of turnover on the achievement of the university's strategic business objectives. | Avoid the loss of institutional knowledge and assure operational continuity to the extent possible.
Management Assists
Follow-up and Resolution of Identified Current Audit Deficiencies | President's Cabinet | Audit Exec | 80 | All Areas | 0 | Ongoing | Support management's response and remediation of reported deficiencies from internal and external authorities. | Mitigate risks identified by audit activities. Assure timely remediation to avoid repeat findings and promote strong relationships with audit authorities.
Evaluate Fraud Risk Control Ratings | CFO | Audit Exec | 80 | Business and Accounting Areas | 0 | September | Support management's efforts to design and implement effective internal controls to deter fraud, waste and abuse. Continue with Procurement and Budget controls. | Avoid fraud, waste and abuse losses.
Time Available to Support Management Assist Requests. | President's Cabinet | Audit Exec | 120 | All Areas | 0 | Ongoing | Support management's efforts to improve the efficiency of operational processes such as time accounting and work orders, comply with external regulation changes, and resolve audit findings. | Support management's continuous improvement of compliance with external regulations and remediation of external audit findings.
Support Annual Financial Statement Audit for DSOs | CFO | Audit Exec | 30 | Accounting | 0 | Ongoing | Support management’s development of internal controls over financial reporting to help avoid material errors. | Mitigate risk of financial report error and perception of university's integrity.
Misconduct Investigations
Conduct Misconduct & Compliance Investigations | Various | Audit Exec | 200 | Various | 0 | As Needed | Conduct investigations of alleged misconduct. | Mitigate risk of SUS Board of Governor's or State Legislature's concern with university leadership stewardship of funding and integrity. Avoid public controversy.
Administration
Develop Audit Committee Agenda Presentations and Minutes | Audit Chairman | Audit Exec | 64 | n/a | 0 | Quarterly | Presentation of Audit, Risk Management, and Compliance efforts to the Audit Committee. | Assures the Audit Committee is well informed of all significant exposures to the achievement of the university's strategic business objectives and compliance with regulatory requirements.
Prepare Annual Internal Audit and Compliance Activities Report | Audit Chairman | Audit Exec | 24 | n/a | 0 | July | Inform the Audit Committee of the Internal Audit and Compliance Department's achievements. | Assure the Internal Audit and Compliance function is effectively operating.
Audit, Risk & Compliance Training | CEO | Audit Exec | 80 | Various | 7000 | Ongoing | Audit Executive obtain continuing education units to stay aware of current industry issues and maintain certifications. Includes university's internal Skillsoft training. | Develop more effective audit, compliance, and risk management programs.
Update Annual Internal Audit, Risk Management and Compliance Plan | Audit Chairman | Audit Exec | 24 | n/a | 0 | June | Utilize Enterprise Risk Assessment to focus Internal Audit and Compliance resources on highest risks to the achievement of the university's objectives. | Assure optimal coverage of the university's significant exposures.
Optional Work
Project Team Participation | President's Cabinet | Audit Exec | 40 | Various | 0 | Ongoing | Support President's Cabinet committee, hiring committees, other requested administration support. | Enhance outcomes of senior leadership strategic initiatives and hiring efforts.
Support Business Continuity Plan Development | Executive Managers | Audit Exec | 40 | Various | 0 | Ongoing | Work with management to develop a meaningful plan to minimize the adverse affects of a disaster. Being ill prepared for a disaster can cost lives, affect customer relations, decrease revenues, and/or increase the cost of operations. We believe the investment is essential to the long-term welfare of the employees and achievement of corporate objectives. | Avoid resource losses associated with loss of data, accessibility, operations, financial reporting, etc., due to nature or malicious disaster(s).
Total Hours |  |  | 2342 |  | 49000
Breakdown of Allocation of Hours
Total Internal Audit Hours |  |  | 800 | 34.16%
Total Compliance Hours |  |  | 584 | 24.94%
Total Risk Management Hours |  |  | 176 | 7.515%
Total Investigations Hours |  |  | 200 | 8.54%
Total Management Assist Hours |  |  | 310 | 13.24%
Total Administrative Hours |  |  | 192 | 8.198%
Total Optional Work Hours |  |  | 80 | 3.416%
Total Hours |  |  | 2342
Proposed Internal Audit Budget
Internal Audit Personnel |  | Potential Hours | Planned Hours | Hour Shortfall | Base Pay (Proposed) | Benefits | Budget Per Line Item
Audit Executive |  | 1686 | 2342 | -656 | 168000 | 67200 | 235200
Proposed Co-sourcing | [6 empty] | 42000
Training and Conferences | [6 empty] | 7000
Travel to State University System Events | [6 empty] | 1500
Office Supplies | [6 empty] | 400
Professional Memberships | [6 empty] | 900
Total Proposed Budget | [6 empty] | 287000
Available Audit Hours Calculation
Hours in Year | 2080
PTO | 274
Administrative* | 120
Total Potential Hours | 1686
* Includes continuing education, performance evaluation, relationship building, standing management meetings, administrative duties, holidays, etc.